## Sheet1
C.E.L.P. Gardens | January |  |  |  | February |  |  |  |  | March |  |  |  |  | April
| Week 1 | Week 2 | Week 3 | Week 4 |  | Week 5 | Week 6 | Week 7 | Week 8 |  | Week 9 | Week 10 | Week 11 | Week 12 |  | Week 13 | Week 14
| 09 Jan - 15 Jan | 16 Jan - 22 Jan | 23 Jan - 29 Jan | 30 Jan - 05 Feb |  | 06 Feb - 12 Feb | 12 Feb - 18 Feb | 20 Feb - 26 Feb | 27 Feb - 05 Mar |  | 06 Mar - 12 Mar | 13 Mar - 19 Mar | 20 Mar - 26 Mar | 27 Mar - 02 Apr |  | 03 Apr - 09 Apr | 10 Apr - 16 Apr
Brainstorm Project Development
Team Biography
Project Summary
Hardware Research
Software Research
Patent & Market Research
Purchase Items
Proposal Report
Algorithm Development
Hardware Integration
Software Testing
Design Review
Testing & Debugging
Final Report & Demonstration
Legend | Team - Cole, Eric, Luke, & Philip |  |  | Research - Cole Moore |  |  |  | Hardware - Eric Messer |  |  |  | Project Lead - Luke Barber |  |  |  | Software - Philip Entrekin